## Cover
Q1 Transformation Summary
Quarter | Phase | Business_Context | Scope | Key_Actions | Approval_Gate | Decision
Q1 | Feasibility, baseline and workforce reset | Direct-to-production failure, high defect, cash burn and proposed business sale | 100 employees; all functions assessed | Hire strategic HRBP; baseline diagnostics; KPI catalogue; cost scenarios; 48-role reset; pilot design | Approve 25-person controlled pilot | Conditional pilot approval

## Scorecard
Q1 KPI Scorecard
Metric | Unit | Q1 | Annual_Target
Overall HR Pillar Maturity Score | Score / 100 | 39 | >=85
Active Headcount | Employees | 52 | 108-118
Time to Fill | Days | 51 | <=30
Offer Acceptance Rate | % | 0.7 | >=85%
Critical Skill Certification | % | 0.32 | >=80%
Compliance Audit Score | % | 0.76 | >=92%
Performance Review Completion | % | 0.49 | >=90%
Recognition Coverage | % | 0.1 | >=70%
Internal Fill Rate | % | 0.06 | >=25%
ER Cases Closed Within SLA | % | 0.48 | >=90%
Quarterly Regrettable Attrition | % | 0.045 | <=3.0%
HR Service SLA Achievement | % | 0.55 | >=90%
HRIS Adoption | % | 0.18 | >=90%
First Pass Yield | % | 0.63 | >=96%
Defect Rate | % | 0.182 | <=3.0%
Units per Labour Hour | Units | 1.04 | >=2.50
Absence Rate | % | 0.071 | <=4.5%
Quarterly Operating Profit | BDT Million | -52.67 | >0

## Workforce Reset
Q1 Role-Based Workforce Reset
Restructuring_ID | Employee_ID | Department | Position | Decision_Date | Effective_Date | Business_Reason | Selection_Criteria | Protected_Attribute_Used | Separation_Benefit_BDT | Estimated_Annual_Cost_Saving_BDT | Critical_Knowledge_Risk | Knowledge_Transfer_Completed | Rehire_Eligible | Ethical_Review_Status
RST-001 | SG-21008062009 | Smartwatch Production | Assembly Operator | 2026-02-01 | 2026-02-11 | Position removed in cost reset | Role need, documented skill match, performance evidence and legal review | No | 35000 | 272400 | Low | Yes | Yes | Reviewed
RST-002 | SG-27024032502 | Finance and Accounts | Costing Analyst | 2026-01-26 | 2026-02-10 | Skill mismatch for precision manufacturing | Role need, documented skill match, performance evidence and legal review | No | 72000 | 695280 | Low | Yes | No | Reviewed
RST-003 | SG-21029082333 | Smartwatch Production | Production Supervisor | 2026-02-20 | 2026-02-28 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 57500 | 919200 | Medium | Yes | No | Reviewed
RST-004 | SG-21022031927 | Smartwatch Production | Assembly Operator | 2026-01-21 | 2026-02-06 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 30750 | 312480 | Medium | Yes | No | Reviewed
RST-005 | SG-21024102301 | Smartwatch Production | Production Line Leader | 2026-03-03 | 2026-03-10 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 74000 | 546720 | High | Yes | Yes | Reviewed
RST-006 | SG-21027072040 | Smartwatch Production | Production Line Leader | 2026-02-08 | 2026-02-18 | Manual role replaced by redesigned process | Role need, documented skill match, performance evidence and legal review | No | 35500 | 517680 | Low | Yes | No | Reviewed
RST-007 | SG-21004102013 | Smartwatch Production | Precision Assembly Technician | 2026-02-09 | 2026-02-24 | Skill mismatch for precision manufacturing | Role need, documented skill match, performance evidence and legal review | No | 56000 | 440880 | High | Yes | No | Reviewed
RST-008 | SG-21012042030 | Smartwatch Production | Precision Assembly Technician | 2026-02-15 | 2026-03-05 | Skill mismatch for precision manufacturing | Role need, documented skill match, performance evidence and legal review | No | 44250 | 431520 | Low | No | Yes | Reviewed
RST-009 | SG-25008102503 | Supply Chain and Planning | Supply Chain Analyst | 2026-02-14 | 2026-02-22 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 100000 | 775200 | High | Yes | No | Reviewed
RST-010 | SG-21009112105 | Smartwatch Production | Precision Assembly Technician | 2026-02-04 | 2026-02-16 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 55000 | 439200 | Low | Yes | Yes | Reviewed
RST-011 | SG-21022112304 | Smartwatch Production | SMT Line Technician | 2026-02-14 | 2026-02-27 | Skill mismatch for precision manufacturing | Role need, documented skill match, performance evidence and legal review | No | 48000 | 374640 | Medium | Yes | Yes | Reviewed
RST-012 | SG-21019031923 | Smartwatch Production | SMT Line Technician | 2026-01-25 | 2026-02-08 | Skill mismatch for precision manufacturing | Role need, documented skill match, performance evidence and legal review | No | 54000 | 405120 | High | Yes | Yes | Reviewed
RST-013 | SG-21007081814 | Smartwatch Production | Assembly Operator | 2026-02-05 | 2026-02-22 | Position removed in cost reset | Role need, documented skill match, performance evidence and legal review | No | 21500 | 332640 | Medium | Yes | Yes | Reviewed
RST-014 | SG-25025042101 | Supply Chain and Planning | Material Planner | 2026-02-02 | 2026-02-10 | Manual role replaced by redesigned process | Role need, documented skill match, performance evidence and legal review | No | 40500 | 623280 | Medium | Yes | Yes | Reviewed
RST-015 | SG-21014122238 | Smartwatch Production | Assembly Operator | 2026-02-19 | 2026-02-27 | Position removed in cost reset | Role need, documented skill match, performance evidence and legal review | No | 30750 | 314880 | Medium | Yes | No | Reviewed
RST-016 | SG-21022041822 | Smartwatch Production | Precision Assembly Technician | 2026-02-15 | 2026-02-26 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 62000 | 485760 | Low | Yes | Yes | Reviewed
RST-017 | SG-21027042115 | Smartwatch Production | Production Line Leader | 2026-02-16 | 2026-02-26 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 32000 | 468720 | Low | Yes | Yes | Reviewed
RST-018 | SG-21014052035 | Smartwatch Production | Assembly Operator | 2026-02-18 | 2026-03-08 | Skill mismatch for precision manufacturing | Role need, documented skill match, performance evidence and legal review | No | 41000 | 304080 | Medium | Yes | Yes | Reviewed
RST-019 | SG-26002032004 | Procurement | Vendor Development Executive | 2026-02-13 | 2026-03-02 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 108000 | 824640 | Low | Yes | Yes | Reviewed
RST-020 | SG-26005022102 | Procurement | Procurement Officer | 2026-02-19 | 2026-02-27 | Skill mismatch for precision manufacturing | Role need, documented skill match, performance evidence and legal review | No | 66000 | 498480 | Medium | Yes | No | Reviewed
RST-021 | SG-25026052202 | Supply Chain and Planning | Material Planner | 2026-02-19 | 2026-03-08 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 42500 | 618000 | Medium | Yes | No | Reviewed
RST-022 | SG-25006072105 | Supply Chain and Planning | Supply Chain Analyst | 2026-02-08 | 2026-02-18 | Skill mismatch for precision manufacturing | Role need, documented skill match, performance evidence and legal review | No | 139000 | 1105920 | Low | Yes | Yes | Reviewed
RST-023 | SG-21027092011 | Smartwatch Production | Production Line Leader | 2026-02-14 | 2026-02-25 | Position removed in cost reset | Role need, documented skill match, performance evidence and legal review | No | 64500 | 634080 | Low | No | Yes | Reviewed
RST-024 | SG-21020121817 | Smartwatch Production | SMT Line Technician | 2026-02-19 | 2026-02-28 | Skill mismatch for precision manufacturing | Role need, documented skill match, performance evidence and legal review | No | 59000 | 459120 | High | Yes | No | Reviewed
RST-025 | SG-31002112302 | Administration and Security | Transport Coordinator | 2026-02-15 | 2026-03-05 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 44250 | 447120 | Low | Yes | No | Reviewed
RST-026 | SG-21012042207 | Smartwatch Production | Assembly Operator | 2026-02-06 | 2026-02-23 | Skill mismatch for precision manufacturing | Role need, documented skill match, performance evidence and legal review | No | 26250 | 271200 | Medium | Yes | Yes | Reviewed
RST-027 | SG-27008102203 | Finance and Accounts | Costing Analyst | 2026-02-12 | 2026-02-22 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 98000 | 775440 | Low | Yes | Yes | Reviewed
RST-028 | SG-21014031912 | Smartwatch Production | Production Line Leader | 2026-02-09 | 2026-02-26 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 40000 | 597600 | Medium | Yes | Yes | Reviewed
RST-029 | SG-12705041803 | Human Resources and People | People Analytics Analyst | 2026-02-15 | 2026-03-05 | Skill mismatch for precision manufacturing | Role need, documented skill match, performance evidence and legal review | No | 92250 | 967440 | Low | Yes | Yes | Reviewed
RST-030 | SG-21023011902 | Smartwatch Production | Production Line Leader | 2026-01-29 | 2026-02-08 | Skill mismatch for precision manufacturing | Role need, documented skill match, performance evidence and legal review | No | 42000 | 642720 | Low | Yes | Yes | Reviewed
RST-031 | SG-21007012306 | Smartwatch Production | Production Supervisor | 2026-02-01 | 2026-02-16 | Position removed in cost reset | Role need, documented skill match, performance evidence and legal review | No | 92000 | 696960 | Medium | Yes | Yes | Reviewed
RST-032 | SG-21007011845 | Smartwatch Production | Assembly Operator | 2026-02-14 | 2026-02-25 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 20000 | 292800 | Low | Yes | No | Reviewed
RST-033 | SG-21029042543 | Smartwatch Production | Assembly Operator | 2026-02-20 | 2026-03-10 | Manual role replaced by redesigned process | Role need, documented skill match, performance evidence and legal review | No | 32250 | 336240 | Medium | Yes | No | Reviewed
RST-034 | SG-21026071916 | Smartwatch Production | Precision Assembly Technician | 2026-02-04 | 2026-02-21 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 54000 | 409920 | Medium | Yes | Yes | Reviewed
RST-035 | SG-29023062202 | Sales Distribution and Service | Warranty Analyst | 2026-02-09 | 2026-02-20 | Skill mismatch for precision manufacturing | Role need, documented skill match, performance evidence and legal review | No | 49000 | 715440 | Medium | No | Yes | Reviewed
RST-036 | SG-21004112432 | Smartwatch Production | Production Supervisor | 2026-01-18 | 2026-02-05 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 53000 | 833280 | Low | No | Yes | Reviewed
RST-037 | SG-30001092002 | EHS and Regulatory Compliance | EHS Officer | 2026-02-10 | 2026-02-17 | Position removed in cost reset | Role need, documented skill match, performance evidence and legal review | No | 61500 | 593760 | Medium | Yes | No | Reviewed
RST-038 | SG-26014051901 | Procurement | Procurement Officer | 2026-02-08 | 2026-02-16 | Position removed in cost reset | Role need, documented skill match, performance evidence and legal review | No | 48000 | 483120 | Low | Yes | Yes | Reviewed
RST-039 | SG-21028021825 | Smartwatch Production | Assembly Operator | 2026-02-18 | 2026-03-08 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 19000 | 281040 | Medium | Yes | Yes | Reviewed
RST-040 | SG-21030102342 | Smartwatch Production | SMT Line Technician | 2026-01-28 | 2026-02-13 | Position removed in cost reset | Role need, documented skill match, performance evidence and legal review | No | 50000 | 399600 | Medium | Yes | Yes | Reviewed
RST-041 | SG-29010112404 | Sales Distribution and Service | Warranty Analyst | 2026-01-28 | 2026-02-08 | Position removed in cost reset | Role need, documented skill match, performance evidence and legal review | No | 98000 | 707040 | Medium | Yes | No | Reviewed
RST-042 | SG-27024112004 | Finance and Accounts | Accounts Officer | 2026-03-02 | 2026-03-10 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 67500 | 709200 | Medium | Yes | Yes | Reviewed
RST-043 | SG-21015012424 | Smartwatch Production | Assembly Operator | 2026-01-28 | 2026-02-09 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 37000 | 274560 | Medium | No | Yes | Reviewed
RST-044 | SG-21014112418 | Smartwatch Production | Production Line Leader | 2026-01-30 | 2026-02-11 | Position removed in cost reset | Role need, documented skill match, performance evidence and legal review | No | 34500 | 531120 | Low | Yes | Yes | Reviewed
RST-045 | SG-21017092019 | Smartwatch Production | Assembly Operator | 2026-02-04 | 2026-02-12 | Skill mismatch for precision manufacturing | Role need, documented skill match, performance evidence and legal review | No | 20000 | 307200 | High | Yes | Yes | Reviewed
RST-046 | SG-12720082301 | Human Resources and People | Talent Acquisition Executive | 2026-02-06 | 2026-02-23 | Skill mismatch for precision manufacturing | Role need, documented skill match, performance evidence and legal review | No | 78000 | 615840 | Medium | Yes | Yes | Reviewed
RST-047 | SG-22008082406 | Quality Assurance | Quality Inspector | 2026-02-23 | 2026-03-06 | Role duplication after line consolidation | Role need, documented skill match, performance evidence and legal review | No | 23000 | 365280 | High | Yes | Yes | Reviewed
RST-048 | SG-30018031801 | EHS and Regulatory Compliance | Regulatory Affairs Specialist | 2026-01-30 | 2026-02-12 | Manual role replaced by redesigned process | Role need, documented skill match, performance evidence and legal review | No | 48000 | 738480 | High | Yes | Yes | Reviewed